Name of Entity: INTERNAL AUDIT AGENCY

PROCUREMENT PLAN (Core budget)

Source of Funding: Government of Liberia

Budget Period/Fiscal year: 2014/2015

| 1 | 2 | 3 | 4 | 5 |  |  | 6 |  | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  | . |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  |  | QTY |  | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS |
| PLANNED | 1 | IFB No. IAA /SS/001/14/15 | Electricity |  | Monthly |  | 35,927.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  | Govt. Entity |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 2 | IFB No. IAA /SS/002/14/15 | Water & Sewage |  | Monthly |  | 1,574.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  | Govt. Entity |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 3 | IFB No. IAA /SS/003/14/15 | Office Rent |  | Yearly |  | 24,000.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  | Multi-Year Ctr |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 4 | IFB No. IAA /SS/004/14/15 | Printing, Binding & Publications |  | Assort. |  | 10,000.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  | Maintain Standard |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 5 | IFB No. IAA /SS/005/14/15 | Gas, Fuel & Lubricant |  | 13,095g |  | 100,606.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 6 | IFB No. IAA /SS/006/14/15 | Rep. & Maint-Auto |  | 5 Vehicles |  | 27,500.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  | Under Wrranty |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 |  | 5 |  | 6 |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 16 |  | 17 | 18 |  | 19 |
|  | Item | Package Number/Code | Contract Package |  | Qty |  | Est. Cost |  |  | Method | Tec. Specs. | Bid Doc. | PC App. 1 | Inv. To Bid | Bid Open | Bid Eval | PC App. 2 | Contr. Awd |  | Adv. Pmt. |  | Delv. | Final Pmt |  | Remarks |
| PLANNED | 7 | IFB No. IAA /SS/007/14/15 | Security Services |  |  |  | 12,600.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 8 | IFB No. IAA /SS/008/14/15 | Employee ID Cards |  |  |  | 750.00 |  |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 9 | IFB No. IAA RFQ /001/14/15 | W/shops, Conferences and Seminars |  | N/A |  | 50,000.00 |  |  | RFQ | 6/3/14 | 6/4/14 | 6/6/14 | 6/13/14 | 6/16/14 | 6/18/14 | 6/20/14 | 6/23/14 |  | N/A |  | 6/15/15 | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 10 | IFB No. IAA RFQ /002/14/15 | Telecom. Internet |  |  |  | 13,200.00 |  |  | RFQ | 11/27/14 | 12/1/15 | 12/3/14 | 12/4/14 | 12/10/14 | 12/12/15 | 12/15/14 | 12/16/14 |  | N/A |  | 12/30/14 | 6/30/15 |  | Changed Provider |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 11 | IFB No. IAA RFQ /003/14/15 | Newspapers, Books and Periodicals |  | 12 Mos. |  | 1,500.00 |  |  | RFQ | N/A | 6/12/14 | 6/12/14 | 6/12/14 | 6/13/14 | 6/14/14 | 6/14/14 | 6/14/14 |  | N/A |  | 6/30/15 | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 12 | IFB No. IAA RFQ /004/14/15 | Operational Expenses |  | N/A |  | 12,000.00 |  |  | RFQ | N/A | 6/12/14 | 6/12/14 | 6/12/14 | 6/13/14 | 6/14/14 | 6/14/14 | 6/14/14 |  | N/A |  | 6/30/15 | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 13 | IFB No. IAA /RB /001/14/15 | Cleaning Materials and Services |  | N/A |  | 24,000.00 |  |  | RB | 6/6/14 | 6/12/14 | 6/12/14 | 6/13/14 | 6/14/14 | 6/14/14 | 6/14/14 | 6/14/14 |  | N/A |  | 6/30/15 | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 14 | IFB No. IAA /RB/002/14/15 | Stationery & Supplies |  | Assort |  | 66,000.00 |  |  | RB | 6/4/14 | 6/6/14 | 6/10/14 | 6/12/14 | 6/19/14 | 6/23/14 | 6/24/14 | 6/26/14 |  | N/A |  | 6/15/15 | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 |  | 5 |  | 6 |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 16 |  | 17 | 18 |  | 19 |
|  | Item | Package Number/Code | Contract Package |  | Qty |  | Est. Cost |  |  | Method | Tec. Specs. | Bid Doc. | PC App. 1 | Inv. To Bid | Bid Open | Bid Eval | PC App. 2 | Contr. Awd |  | Adv. Pmt. |  | Delv. | Final Pmt |  | Remarks |
| PLANNED | 15 | IFB No. IAA /RB/003/14/15 | Furniture & Fixtures |  | Assort |  | 22,000.00 |  |  | RB | 6/6/14 | 6/12/14 | 6/9/14 | 6/10/14 | 6/17/14 | 6/19/14 | 6/23/14 | 6/25/14 |  | N/A |  | 6/15/15 | 6/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  |  | $401,657.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared by: ___________________________________				Approved by: ________________________________________	    Date: ________________

Procurement Director/ Manager                                                                                       Head of Entity/Chairman Proc. Committee