## LEG PLAN 2014-2015
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 1 | IFBNO./LACE/RB/001/2014/2015 | Petroleum Product -( Vehicle & Generator) | 17201.8349 | 75000 | RB | 2014-08-01 | 2014-08-22 | 2014-08-29 | 2014-09-05 | 2014-10-03 | 2014-10-10 | 2014-10-17 | 2014-10-31 | N/A | 2014-11-14 | 2015-06-30
UPDATE
ACTUAL
| PLANNED | 2 | IFBNO/LACE/NCB/001/2014/2015 | Vehicle (4X4 - Jeep) | 3 | 150000 | NCB | 2014-11-01 | 2014-11-08 | 2014-11-15 | 2014-11-22 | 2014-12-20 | 2014-12-27 | 2015-01-03 | 2015-01-10 | N/A | 2015-01-24 | 2015-02-21
UPDATE
ACTUAL
| PLANNED | 3 | IFBNO./LACE/RFQ/001/2014/2015 | Generator (3.5 KVA) | 2 | 3500 | RFQ | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | N/A | 2015-02-09 | 2015-02-23
UPDATE
ACTUAL
| PLANNED | 4 | IFBNO./LACE/RFQ/002/2014/2015 | Laptop Computer (including accessories & cartridges) | Assorted | 8000 | RFQ | 2014-12-16 | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-03 | N/A | 2015-02-10 | 2015-02-24
UPDATE
ACTUAL
Goods & Services
| PLANNED | 5 | IFBNO./LACE/NCB/002/2014/2015 | Vehicle Repair & Maintenance/Spare parts (Jeep) | 16 | 44750 | NCB | 2015-03-05 | 2015-03-12 | 2015-03-19 | 2015-03-26 | 2015-04-23 | 2015-04-30 | 2015-05-07 | 2015-05-14 | N/A | 2015-05-28 | 2015-06-25
UPDATE
ACTUAL
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 6 | IFBNO./LACE/NCB/03/2014/2015 | Generator Repair & Maintenance/Spare parts | 4 | 10750 | NCB | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | 2015-03-31 | 2015-04-07 | 2015-04-14 | 2015-04-21 | N/A | 2015-05-05 | 2015-06-02
UPDATE
ACTUAL
| PLANNED | 7 | IFBNO./LACE/RFQ/003/2014/2015 | Stationery | Assorted* | 2500 | RFQ | 2015-04-19 | 2015-04-26 | 2015-05-03 | 2015-05-10 | 2015-05-17 | 2015-05-24 | 2015-05-31 | 2015-06-07 | N/A | 2015-06-14 | 2015-06-28
UPDATE
ACTUAL
| PLANNED | 8 | IFBNO./LACE/RFQ/004/2014/2015 | Janitorial materials | Assorted* | 1500 | RFQ | 2015-04-09 | 2015-04-16 | 2015-04-23 | 2015-04-30 | 2015-05-07 | 2015-05-14 | 2015-05-21 | 2015-05-28 | N/A | 2015-06-04 | 2015-06-18
UPDATE
ACTUAL
UPDATE
| ACTUAL |  | Sub-total |  |  | 296000
Small Works
| PLANNED | 9 | IFBNO./LACE/NCB/004/2014/2015 | Gbelay-Geh School System | 1 | 150000 | NCB | 2014-08-10 | 2014-08-17 | 2014-08-24 | 2014-08-31 | 2014-09-28 | 2014-10-05 | 2014-10-12 | 2014-10-19 | N/A | 2015-01-11 | 2015-06-28
UPDATE
ACTUAL
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 10 | IFBNO./LACE/NCB/005/2014/2015 | Garplay Junior High School | 1 | 39750 | NCB | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | N/A | 2015-02-02 | 2015-07-20
UPDATE
ACTUAL
| PLANNED | 11 | IFBNO./LACE/NCB/006/2014/2015 | Sanniquellie Central High School | 1 | 100000 | NCB | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | N/A | 2015-02-02 | 2015-07-20
UPDATE
ACTUAL
| PLANNED | 12 | IFB/LACE/RFQ/007/2014/2015 | Ganta City Hall | 1 | 26500 | RFQ | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | N/A | 2014-12-15 | 2015-01-12
UPDATE
ACTUAL
| PLANNED | 13 | IFBNO./LACE/NCB/007/2014/2015 | Gboveh High School | 1 | 150000 | NCB | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | N/A | 2015-02-02 | 2015-07-20
UPDATE
ACTUAL
| PLANNED | 14 | IFBNO./LACE/RFQ/008/2014/2015 | Gbatala Public School | 1 | 25000 | RFQ | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | N/A | 2014-12-15 | 2015-01-12
UPDATE
ACTUAL
| PLANNED | 15 | IFB/LACE/NCB/008/2014/2015 | William V. S. Tubman Gray High School | 1 | 39500 | NCB | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | N/A | 2015-02-02 | 2015-07-20
UPDATE
ACTUAL
| PLANNED | 16 | IFBNO./LACE/RFQ/009/2014/2015 | N. V. MASSAQUOI | 1 | 26500 | RFQ | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | N/A | 2014-12-15 | 2015-01-12
UPDATE
ACTUAL
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 17 | IFBNO./LACE/RFQ/010/2014/2015 | Janjay Public School | 1 | 26500 | RFQ | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-11-12 | 2014-11-19 | N/A | 2015-01-14 | 2015-02-11
UPDATE
ACTUAL
| PLANNED | 18 | IFBNO./LACE/RFQ/011/2014/2015 | Muslim Youth School | 1 | 26500 | RFQ | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-11-12 | 2014-11-19 | N/A | 2015-01-14 | 2015-02-11
UPDATE
ACTUAL
| PLANNED | 19 | IFBNO./LACE/NCB/009/2014/2015 | Yanquoi Bee Audiorium | 1 | 100000 | NCB | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-10-22 | 2014-11-19 | 2014-11-26 | 2014-12-03 | 2014-12-10 | N/A | 2015-03-04 | 2015-08-19
UPDATE
ACTUAL
| PLANNED | 20 | IFBNO./LACE/NCB/010/2014/2015 | Sammy Youth Center | 1 | 39750 | NCB | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-10-22 | 2014-11-19 | 2014-11-26 | 2014-12-03 | 2014-12-10 | N/A | 2015-03-04 | 2015-08-19
UPDATE
ACTUAL
| PLANNED | 21 | IFBNO./LACE/RFQ/012/2014/2015 | Foloblio Town Hall | 1 | 26500 | RFQ | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-11-12 | 2014-11-19 | N/A | 2015-01-14 | 2015-02-11
UPDATE
ACTUAL
| PLANNED | 22 | IFBNO./LACE/RFQ/013/2014/2015 | Wainsue Comm. Compound | 1 | 26500 | RFQ | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-11-12 | 2014-11-19 | N/A | 2015-01-14 | 2015-02-11
UPDATE
ACTUAL
| PLANNED | 23 | IFBNO./LACE/NCB/011/2014/2015 | Seebeh Community Clinic | 1 | 40000 | NCB | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-10-22 | 2014-11-19 | 2014-11-26 | 2014-12-03 | 2014-12-10 | N/A | 2015-03-04 | 2015-08-19
UPDATE
ACTUAL
| PLANNED | 24 | IFBNO./LACE/RFQ/014/2014/2015 | Morioquelleh Town Hall | 1 | 26500 | RFQ | 2014-11-15 | 2014-11-22 | 2014-11-29 | 2014-12-06 | 2014-12-13 | 2014-12-20 | 2014-12-27 | 2015-01-03 | N/A | 2015-02-28 | 2015-03-28
UPDATE
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST |  | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 25 | IFBNO./LACE/NCB/012/2014/2015 | Gbarnga Central Market | 1 | 53000 | NCB | 2014-11-15 | 2014-11-22 | 2014-11-29 | 2014-12-06 | 2015-01-03 | 2015-01-10 | 2015-01-17 | 2015-01-24 | N/A | 2015-04-18 | 2015-10-03
UPDATE
ACTUAL
| PLANNED | 26 | IFBNO./LACE/NCB/013/2014/2015 | Peter Town Guest House | 1 | 50000 | NCB | 2014-11-15 | 2014-11-22 | 2014-11-29 | 2014-12-06 | 2015-01-03 | 2015-01-10 | 2015-01-17 | 2015-01-24 | N/A | 2015-04-18 | 2015-10-03
UPDATE
ACTUAL
| PLANNED | 27 | IFBNO./LACE/NCB/014/2014/2015 | Yanweullie Town Hall | 1 | 40000 | NCB | 2014-11-15 | 2014-11-22 | 2014-11-29 | 2014-12-06 | 2015-01-03 | 2015-01-10 | 2015-01-17 | 2015-01-24 | N/A | 2015-04-18 | 2015-10-03
UPDATE
ACTUAL
| PLANNED | 28 | IFBNO./LACE/NCB/015/2014/2015 | Dokoita Public School | 1 | 100000 | NCB | 2014-11-15 | 2014-11-22 | 2014-11-29 | 2014-12-06 | 2015-01-03 | 2015-01-10 | 2015-01-17 | 2015-01-24 | N/A | 2015-04-18 | 2015-10-03
UPDATE
ACTUAL
| PLANNED | 29 | IFBNO./LACE/NCB/016/2014/2015 | Wenwuta Public School | 1 | 100000 | NCB | 2014-11-25 | 2014-12-02 | 2014-12-09 | 2014-12-16 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-03 | N/A | 2015-04-28 | 2015-10-13
UPDATE
ACTUAL
| PLANNED | 30 | IFBNO./LACE/NCB/017/2014/2015 | Sumokota High School | 1 | 45000 | NCB | 2014-11-25 | 2014-12-02 | 2014-12-09 | 2014-12-16 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-03 | N/A | 2015-04-28 | 2015-10-13
| PLANNED | 31 | IFB/LACE/RFQ/015/2014/2015 | Kolahun Youth Center | 1 | 26500 | RFQ | 2014-11-25 | 2014-12-02 | 2014-12-09 | 2014-12-16 | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | N/A | 2015-03-10 | 2015-04-07
| PLANNED | 32 | IFBNO./LACE/NCB/018/2014/2015 | Bensville Road | 1 | 45000 | NCB | 2014-11-25 | 2014-12-02 | 2014-12-09 | 2014-12-16 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-03 | N/A | 2015-04-28 | 2015-10-13
UPDATE
| PLANNED | 33 | IFBNO./LACE/NCB/019/2014/2015 | Zorzor Central High School | 1 | 50000 | NCB | 2014-11-25 | 2014-12-02 | 2014-12-09 | 2014-12-16 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-03 | N/A | 2015-04-28 | 2015-10-13
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 34 | IFBNO./LACE/NCB/020/2014/2015 | Salayea Central high School | 1 | 50000 | NCB | 2014-11-25 | 2014-12-02 | 2014-12-09 | 2014-12-16 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-03 | N/A | 2015-04-28 | 2015-10-13
UPDATE
ACTUAL
| PLANNED | 35 | IFBNO./LACE/RFQ/016/2014/2015 | Gbarma Youth Center | 1 | 26500 | RFQ | 2014-12-05 | 2014-12-12 | 2014-12-19 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-16 | 2015-01-23 | N/A | 2015-03-20 | 2015-04-17
UPDATE
ACTUAL
| PLANNED | 36 | IFB/LACE/NCB/021/2014/2015 | Cestor Central high School | 1 | 100000 | NCB | 2014-12-05 | 2014-12-12 | 2014-12-19 | 2014-12-26 | 2015-01-23 | 2015-01-30 | 2015-02-06 | 2015-02-13 | N/A | 2015-05-08 | 2015-10-23
UPDATE
| PLANNED | 37 | IFBNO./LACE/NCB/022/2014/2015 | Than Market Hall | 1 | 39750 | NCB | 2014-12-05 | 2014-12-12 | 2014-12-19 | 2014-12-26 | 2015-01-23 | 2015-01-30 | 2015-02-06 | 2015-02-13 | N/A | 2015-05-08 | 2015-10-23
UPDATE
| PLANNED | 38 | IFBNO./LACE/NCB/023/2014/2015 | Voinjama Multilateral | 1 | 50000 | NCB | 2014-12-05 | 2014-12-12 | 2014-12-19 | 2014-12-26 | 2015-01-23 | 2015-01-30 | 2015-02-06 | 2015-02-13 | N/A | 2015-05-08 | 2015-10-23
| PLANNED | 39 | IFBNO./LACE/NCB/024/2014/2015 | Lofa Community Ciollage | 1 | 100000 | NCB | 2014-12-05 | 2014-12-12 | 2014-12-19 | 2014-12-26 | 2015-01-23 | 2015-01-30 | 2015-02-06 | 2015-02-13 | N/A | 2015-05-08 | 2015-10-23
UPDATE
| PLANNED | 40 | IFBNO./LACE/NCB/025/2014/2015 | Sinoe Multilateral High School | 1 | 100000 | NCB | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | N/A | 2015-05-18 | 2015-11-02
UPDATE
ACTUAL
| PLANNED | 41 | IFBNO./LACE/RFQ/017/2014/2015 | Zordee Town Hall | 1 | 26500 | RFQ | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | N/A | 2015-03-30 | 2015-04-27
UPDATE
| PLANNED | 42 | IFBNO./LACE/RFQ/018/2014/2015 | Tewor Chief Compound | 1 | 26500 | RFQ | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | N/A | 2015-03-30 | 2015-04-27
UPDATE
ACTUAL
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 43 | IFBNO./LACE/NCB/026/2014/2015 | Kolleh Town Public School | 1 | 100000 | NCB | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | N/A | 2015-05-18 | 2015-11-02
UPDATE
| PLANNED | 44 | IFBNO./LACE/NCB/027/2014/2015 | Konia Women Center | 1 | 39750 | NCB | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | N/A | 2015-05-18 | 2015-11-02
UPDATE
| PLANNED | 45 | IFBNO./LACE/RFQ/019/2014/2015 | Gbajake Town Hall | 1 | 26500 | RFQ | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | N/A | 2015-03-30 | 2015-04-27
UPDATE
| PLANNED | 46 | IFBNO./LACE/NCB/028/2014/2015 | Saygba Cole Musulim School | 1 | 66250 | NCB | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | N/A | 2015-05-26 | 2015-11-10
UPDATE
| PLANNED | 47 | IFBNO./LACE/NCB/029/2014/2015 | William T. Savage School | 1 | 100000 | NCB | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | N/A | 2015-05-26 | 2015-11-10
UPDATE
| PLANNED | 48 | IFB/LACE/NCB/030/2014/2015 | Jacob Town School | 1 | 100000 | NCB | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | N/A | 2015-05-26 | 2015-11-10
UPDATE
| PLANNED | 49 | IFBNO./LACE/NCB/031/2014/2015 | Pokpa Youth Center | 1 | 39750 | NCB | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | N/A | 2015-05-26 | 2015-11-10
UPDATE
| PLANNED | 50 | IFBNO./LACE/RFQ/020/2014/2015 | Manakoma | 1 | 26500 | RFQ | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-03 | 2015-02-10 | N/A | 2015-04-07 | 2015-05-05
UPDATE
ACTUAL
| PLANNED | 51 | IFBNO./LACE/NCB/032/2014/2015 | Weala Public High School | 1 | 500000 | NCB | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | N/A | 2015-05-26 | 2015-11-10
UPDATE
ACTUAL
| PLANNED | 52 | IFBNO./LACE/NCB/033/2014/2015 | Guzeh Public School | 1 | 45000 | NCB | 2014-12-23 | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | N/A | 2015-05-26 | 2015-11-10
UPDATE
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Goods & Services
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| ACTUAL |  | Sub-total |  |  | 2942000
GRAND TOTAL (GOODS, SMALL WORKS, & NON-CONSULTANT SERVICES) | [5 empty] | 3238000
| PLANNED |  | Total
UPDATE
ACTUAL
#VALUE! |  |  | Prepared By: _________________________________ |  |  |  |  | 2014-12-23: Dae:______________________________; 2015-02-17: Approved By: ________________________________
|  |  |  | Kornema Y. Mulbah |  |  |  | 2015-02-24: Julius K. Sele
|  |  |  | Senior Procurement Officer |  |  |  | 2015-02-24: Executive Director
LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT
PROCUREMENT PLAN
LEGISLATURE PROJECT
July 1, 2014 - June 30, 2015
NOTE: SUMMARY BUDGET:
|  |  |  | Goods, Small Works, and Non-Consultancy Services |  |  | 2942000
|  |  |  | Administrative Administrative Expenditure: |  |  |  | 2015-02-17: -4000
|  |  |  | Operational Expenses |  |  | 300000
|  |  |  | Total |  |  | 3242000
Formulas:
Delivery = [Contract Award/Signing]+14
Delivery = [Contract Award/Signing]+(2*7)
Final Payment = [Delivery]+228
Final Payment = [Delivery]+(4*7)

## Funding sources-2011-2012
FUNDING SOURCES
| Description | ITEM CODE | GOL | AfDB | YES | WORLD BANK | YEP | OTHER DONORS | TOTAL
1 | Diesel Fuel & Gasoline | IFB/LACE/NCB/001/2012/2013 | 531409 | 368591 | 300000 | 400000 |  |  | 1600000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
11 | [8 empty] | 0
12 | [8 empty] | 0
13 | [8 empty] | 0
14 | [8 empty] | 0
15 | [8 empty] | 0
16 | [8 empty] | 0
17 | [8 empty] | 0
18 | [8 empty] | 0
19 | [8 empty] | 0
20 | [8 empty] | 0
21 | [8 empty] | 0
22 | [8 empty] | 0
23 | [8 empty] | 0
24 | [8 empty] | 0
25 | [8 empty] | 0
26 | [8 empty] | 0
27 | [8 empty] | 0
28 | [8 empty] | 0
29 | [8 empty] | 0
30 | [8 empty] | 0
31 | [8 empty] | 0
32 | [8 empty] | 0
33 | [8 empty] | 0
34 | [8 empty] | 0
35 | [8 empty] | 0
36 | [8 empty] | 0
37 | [8 empty] | 0
38 | [8 empty] | 0
GRAND TOTAL | [8 empty] | 1600000